## Product Backlog
PRODUCT BACKLOG ¦ City General Hospital IVR
AI-Enabled Conversational IVR Modernization ¦ Patient Admission and Bed Availability ¦ Feb 02 to Apr 02 2025
Story ID | Planned Sprint | Actual Sprint | User Story Description | MoSCoW | Dependency | Assignee | Status | Remarks
US-001 | Pre-Sprint | Pre-Sprint | As a project lead I want the team assigned to a subtopic with clear scope so that development can begin without ambiguity. Subtopic: Patient Admission and Bed Availability. | Must Have | None | Ayush | Completed | Assigned Feb 02 — kickoff complete
US-002 | Sprint 1 | Sprint 1 | As a system architect I want to design the five-layer IVR architecture (STT to NLU to Session to TTS to Flow) with technology selection justified so the development team has a clear blueprint. | Must Have | US-001 | Ayush | Completed | M1 deliverable — submitted Feb 16
US-003 | Sprint 1 | Sprint 1 | As a hospital developer I want all /ivr/* API contracts documented before coding begins so that endpoints are consistent and testable from day one. | Must Have | US-002 | Ayush | Completed | 15 endpoints documented in M1 contract doc
US-004 | Sprint 1 | Sprint 1 | As a hospital administrator I want a working mock database with 8 wards and 4 patients so that all IVR flows have realistic data to query during development and demo. | Must Have | US-002 | Ayush | Completed | hospital_db.py with 8 wards 4 patients admission queue
US-005 | Sprint 1 | Sprint 1 | As a caller I want a DTMF button-press IVR with 5 menu flows (beds admission status ward info agent) so I can access hospital services by pressing numbered options. | Must Have | US-003 | Ayush | Completed | M2 deliverable — DTMF IVR submitted Mar 02
US-006 | Sprint 2 | Sprint 2 | As a caller I want to speak naturally to the hospital IVR instead of pressing buttons so I can describe my need in my own words — especially useful for elderly and emergency callers. | Must Have | US-005 | Ayush | Completed | Twilio Gather input=dtmf speech with en-IN language
US-007 | Sprint 2 | Sprint 2 | As a hospital system I want GPT-3.5 to detect the caller intent and extract entities (ward name patient ID urgency level) from natural speech so the IVR routes accurately. | Must Have | US-006 | Ayush | Completed | nlu_service.py: GPT-3.5 plus keyword fallback plus alias normaliser
US-008 | Sprint 2 | Sprint 2 | As a hospital system I want a keyword-based NLU fallback so the IVR continues working even when the OpenAI API is unavailable without the caller knowing anything is wrong. | Must Have | US-007 | Ayush | Completed | Automatic fallback in detect_intent via try/except
US-009 | Sprint 2 | Sprint 2 | As a caller I want to hear natural Indian-accented voice responses with proper pauses and pronunciation of patient IDs so the IVR feels professional and easy to understand. | Must Have | US-006 | Ayush | Completed | Amazon Polly Aditi plus SSML breaks spell-out emphasis prosody
US-010 | Sprint 2 | Sprint 2 | As a caller completing an admission request I want the IVR to remember my earlier answers (patient name ward urgency) across multiple turns so I do not have to repeat myself. | Must Have | US-006 | Ayush | Completed | session_manager.py: CallSid-keyed dict with set/get_collected
US-011 | Sprint 2 | Sprint 2 | As a family member I want to admit a patient via a 4-step conversational flow (name then ward then urgency then confirm) so the admission process is fast and clear even during stressful situations. | Must Have | US-010 | Ayush | Completed | 4-step multi-turn: /ivr/admission/name ward urgency confirm
US-012 | Sprint 3 | Sprint 3 | As a security engineer I want every Twilio webhook request validated using HMAC-SHA1 signature before it reaches any IVR handler so that fake requests cannot trigger the system. | Must Have | US-005 | Ayush | Completed | TwilioSignatureMiddleware: enforce/log_only/disabled modes
US-013 | Sprint 3 | Sprint 3 | As an IVR operator I want callers who cannot be understood after 3 consecutive failures to be automatically transferred to a human agent so no caller is abandoned. | Must Have | US-007 | Ayush | Completed | retry_count >= MAX_RETRIES triggers transfer_to_agent_twiml
US-014 | Sprint 3 | Sprint 3 | As an IVR system I want low-confidence speech below 0.65 to trigger a confirmation gate before acting on the intent so the system does not misroute callers on unclear speech. | Must Have | US-007 | Ayush | Completed | Confidence gating with confirm/deny TwiML loop
US-015 | Sprint 3 | Sprint 3 | As a hospital operator I want admin monitoring endpoints for status beds patients and sessions so I can inspect live system state during a demo without touching the code. | Should Have | US-004 | Ayush | Completed | admin_router.py — 7 monitoring endpoints
US-016 | Sprint 3 | Sprint 3 | As a DevOps engineer I want the hospital IVR deployed to Render with HTTPS and the Twilio phone number webhook configured so real test calls can be made to validate the system. | Must Have | US-012 | Ayush | Completed | Deployed to Render; Twilio webhook to /ivr/welcome
US-017 | Sprint 4 | Sprint 4 | As a QA engineer I want a unit test suite with 67 test cases covering all endpoints in isolation with GPT mocked so every route handler is validated without making real API calls. | Must Have | US-011 | Ayush | Completed | test_unit.py: 67 TCs across M1-M4 12 test classes
US-018 | Sprint 4 | Sprint 4 | As a QA engineer I want integration tests verifying multi-turn session persistence and all patient lookups so bugs that only appear when components interact are caught. | Must Have | US-010 | Ayush | Completed | test_integration.py: 5 classes session DB and flow tests
US-019 | Sprint 4 | Sprint 4 | As a QA engineer I want E2E tests simulating complete caller journeys (happy path DTMF escalation multi-flow) so real user experiences are validated end to end. | Must Have | US-013 | Ayush | Completed | test_e2e.py: 4 full journeys plus performance tests
US-020 | Sprint 4 | Sprint 4 | As a hospital operations manager I want performance tests confirming webhook response time under 2s and 20 concurrent requests all succeed so Twilio SLAs are always met. | Must Have | US-017 | Ayush | Completed | TestPerformance: latency load 20-request and 3-thread concurrent
US-021 | Sprint 4 | Sprint 4 | As a project manager I want a complete defect tracker unit test plan and agile template covering all milestones submitted as M4 artifacts. | Must Have | US-017 | Ayush | Completed | 3 Excel artifacts submitted with M4
US-022 | Sprint 4 | Sprint 4 | As a caller who speaks Hindi I want the IVR to understand and respond in Hindi so non-English-speaking patients can access hospital services. | Could Have | US-009 | Ayush | Not Started | Future: Twilio hi-IN plus Polly Hindi
US-023 | Sprint 4 | Sprint 4 | As a caller who completed an admission request I want to receive an SMS with my REQ reference number so I have the confirmation in writing. | Could Have | US-011 | Ayush | Not Started | Future: Twilio Messaging API
US-024 | Sprint 4 | Sprint 4 | As a developer I want the session store replaced with Redis so the IVR can scale horizontally across multiple instances without session data loss on restart. | Should Have | US-010 | Ayush | Not Started | Session manager interface is already Redis-compatible

## Sprint Backlog
SPRINT BACKLOG ¦ City General Hospital IVR
NOTE: Task sizing is between 0.5 to 12 hours per task
Task ID | Sprint | Story Ref | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Est. Hours | Status
T-001 | Sprint 1 | US-001 | Project kickoff: confirm subtopic set up GitHub repo create folder structure | 02 Feb 2025 | 02 Feb 2025 | Ayush | Project Setup | 2 | Completed
T-002 | Sprint 1 | US-002 | Design 5-layer IVR architecture diagram STT to NLU to Session to TTS to Flow | 02 Feb 2025 | 04 Feb 2025 | Ayush | Architecture | 6 | Completed
T-003 | Sprint 1 | US-002 | Compare and select technologies: Twilio vs Azure vs Web Simulator with justification | 04 Feb 2025 | 05 Feb 2025 | Ayush | Architecture | 4 | Completed
T-004 | Sprint 1 | US-003 | Document API contracts for all 15 /ivr/* endpoints before any coding | 05 Feb 2025 | 07 Feb 2025 | Ayush | Documentation | 5 | Completed
T-005 | Sprint 1 | US-004 | Create hospital_db.py with 8 wards 4 patients and admission request queue | 07 Feb 2025 | 09 Feb 2025 | Ayush | Backend Dev | 4 | Completed
T-006 | Sprint 1 | US-005 | Build FastAPI app skeleton: main.py routers lifespan CORS middleware | 09 Feb 2025 | 10 Feb 2025 | Ayush | Backend Dev | 5 | Completed
T-007 | Sprint 1 | US-005 | Implement DTMF routing for digits 0-4 in /ivr/intent endpoint | 10 Feb 2025 | 12 Feb 2025 | Ayush | Backend Dev | 5 | Completed
T-008 | Sprint 1 | US-005 | Build all 5 DTMF IVR flows: bed availability admission status ward inquiry agent transfer | 12 Feb 2025 | 14 Feb 2025 | Ayush | Backend Dev | 8 | Completed
T-009 | Sprint 1 | US-005 | Set up ngrok and Twilio webhook then verify all 5 DTMF flows with live calls | 14 Feb 2025 | 16 Feb 2025 | Ayush | Integration | 4 | Completed
T-010 | Sprint 2 | US-006 | Migrate all Gather from numDigits to input=dtmf speech with en-IN and hospital hints | 16 Feb 2025 | 18 Feb 2025 | Ayush | Backend Dev | 4 | Completed
T-011 | Sprint 2 | US-006 | Add hospital domain hints to all Gather tags: ward names urgency terms patient IDs | 18 Feb 2025 | 18 Feb 2025 | Ayush | Backend Dev | 2 | Completed
T-012 | Sprint 2 | US-007 | Build nlu_service.py: GPT-3.5 system prompt JSON output intent and entity extraction | 19 Feb 2025 | 22 Feb 2025 | Ayush | AI/NLU Dev | 10 | Completed
T-013 | Sprint 2 | US-007 | Build WARD_ALIASES dict: map heart ward cardiac brain to canonical ward keys | 22 Feb 2025 | 22 Feb 2025 | Ayush | AI/NLU Dev | 2 | Completed
T-014 | Sprint 2 | US-008 | Implement keyword fallback in detect_intent via try/except around GPT call | 22 Feb 2025 | 23 Feb 2025 | Ayush | AI/NLU Dev | 4 | Completed
T-015 | Sprint 2 | US-009 | Migrate all Say tags to Polly.Aditi with language=en-IN attribute | 23 Feb 2025 | 24 Feb 2025 | Ayush | TTS/SSML | 3 | Completed
T-016 | Sprint 2 | US-009 | Add SSML: break tags say-as spell-out emphasis and prosody rate=slow | 24 Feb 2025 | 26 Feb 2025 | Ayush | TTS/SSML | 5 | Completed
T-017 | Sprint 2 | US-010 | Build session_manager.py: get/set/update/end session collected data retry counter | 26 Feb 2025 | 27 Feb 2025 | Ayush | Backend Dev | 5 | Completed
T-018 | Sprint 2 | US-011 | Implement 4-step admission flow with session persistence across all turns | 27 Feb 2025 | 01 Mar 2025 | Ayush | Backend Dev | 8 | Completed
T-019 | Sprint 2 | US-011 | Build post-action handler and call-status webhook for session cleanup | 01 Mar 2025 | 02 Mar 2025 | Ayush | Backend Dev | 3 | Completed
T-020 | Sprint 3 | US-012 | Build TwilioSignatureMiddleware with HMAC-SHA1 validation algorithm | 02 Mar 2025 | 05 Mar 2025 | Ayush | Security | 8 | Completed
T-021 | Sprint 3 | US-012 | Add 3-mode config: enforce/log_only/disabled via TWILIO_VALIDATION_MODE env var | 05 Mar 2025 | 06 Mar 2025 | Ayush | Security | 3 | Completed
T-022 | Sprint 3 | US-012 | Add compute_test_signature utility for generating valid test signatures | 06 Mar 2025 | 06 Mar 2025 | Ayush | Security | 2 | Completed
T-023 | Sprint 3 | US-013 | Implement retry counter in session plus MAX_RETRIES=3 escalation to agent | 07 Mar 2025 | 08 Mar 2025 | Ayush | Backend Dev | 4 | Completed
T-024 | Sprint 3 | US-014 | Build low-confidence gating: below 0.65 triggers confirmation TwiML before acting | 08 Mar 2025 | 09 Mar 2025 | Ayush | Backend Dev | 3 | Completed
T-025 | Sprint 3 | US-015 | Build admin_router.py: /admin/status /beds /patients /sessions /security | 09 Mar 2025 | 11 Mar 2025 | Ayush | Backend Dev | 5 | Completed
T-026 | Sprint 3 | US-016 | Deploy FastAPI app to Render with HTTPS configure env vars via dashboard | 11 Mar 2025 | 14 Mar 2025 | Ayush | DevOps | 5 | Completed
T-027 | Sprint 3 | US-016 | Configure Twilio phone number webhook to production Render URL | 14 Mar 2025 | 15 Mar 2025 | Ayush | DevOps | 2 | Completed
T-028 | Sprint 3 | US-016 | Live call verification: test all 4 IVR flows via real Twilio calls on Render | 15 Mar 2025 | 16 Mar 2025 | Ayush | QA/Testing | 3 | Completed
T-029 | Sprint 4 | US-017 | Set up conftest.py: session clear fixture env vars TestClient factory | 16 Mar 2025 | 17 Mar 2025 | Ayush | Testing | 3 | Completed
T-030 | Sprint 4 | US-017 | Write TestRootEndpoints TestIVRWelcome TestMainMenu — 12 test cases | 17 Mar 2025 | 18 Mar 2025 | Ayush | Testing | 4 | Completed
T-031 | Sprint 4 | US-017 | Write TestIntentRouterDTMF TestIntentRouterSpeech — 12 test cases GPT mocked | 18 Mar 2025 | 19 Mar 2025 | Ayush | Testing | 5 | Completed
T-032 | Sprint 4 | US-017 | Write TestBedAvailability TestAdmissionFlow TestPatientStatus — 10 test cases | 19 Mar 2025 | 20 Mar 2025 | Ayush | Testing | 5 | Completed
T-033 | Sprint 4 | US-017 | Write TestWardInquiry 8 wards parametrized TestAdminEndpoints — 11 test cases | 20 Mar 2025 | 20 Mar 2025 | Ayush | Testing | 3 | Completed
T-034 | Sprint 4 | US-017 | Write TestErrorHandling TestSessionManager — 9 test cases | 21 Mar 2025 | 21 Mar 2025 | Ayush | Testing | 4 | Completed
T-035 | Sprint 4 | US-018 | Write integration tests: 2-turn bed flow 4-step admission session verification | 21 Mar 2025 | 23 Mar 2025 | Ayush | Testing | 7 | Completed
T-036 | Sprint 4 | US-018 | Write integration tests: patient lookup by ID and name post-action flow | 23 Mar 2025 | 24 Mar 2025 | Ayush | Testing | 4 | Completed
T-037 | Sprint 4 | US-019 | Write E2E Flow 1: full admission happy path with REQ reference assertion | 24 Mar 2025 | 25 Mar 2025 | Ayush | Testing | 5 | Completed
T-038 | Sprint 4 | US-019 | Write E2E Flow 2 DTMF Flow 3 three-strike escalation Flow 4 multi-flow | 25 Mar 2025 | 26 Mar 2025 | Ayush | Testing | 6 | Completed
T-039 | Sprint 4 | US-020 | Write performance tests: latency assertions 20-request load 3-thread concurrent | 26 Mar 2025 | 27 Mar 2025 | Ayush | Testing | 4 | Completed
T-040 | Sprint 4 | US-021 | Create Unit Test Plan Excel: 67 TCs across M1-M4 summary and per-milestone sheets | 27 Mar 2025 | 28 Mar 2025 | Ayush | Documentation | 5 | Completed
T-041 | Sprint 4 | US-021 | Create Defect Tracker Excel: 30 defects all sprints summary tab | 28 Mar 2025 | 29 Mar 2025 | Ayush | Documentation | 4 | Completed
T-042 | Sprint 4 | US-021 | Create Agile Template Excel: product backlog sprint backlog standup retro timeline | 29 Mar 2025 | 30 Mar 2025 | Ayush | Documentation | 5 | Completed
T-043 | Sprint 4 | US-016 | Set TWILIO_VALIDATION_MODE=enforce in Render production dashboard | 30 Mar 2025 | 30 Mar 2025 | Ayush | Security/DevOps | 1 | Completed
T-044 | Sprint 4 | US-019 | Final demo: run all 4 live IVR flows for panel — admission bed status escalation | 30 Mar 2025 | 02 Apr 2025 | Ayush | QA/Demo | 4 | Completed

## Stand-up Meeting
DAILY STAND-UP LOG ¦ City General Hospital IVR
Date | Sprint | Done Yesterday | Plan Today | Impediments | Action Taken / Notes
02 Feb 2025 | Sprint 1 | Project kickoff GitHub repo created subtopic confirmed as Patient Admission and Bed Availability | Design 5-layer IVR architecture diagram | None | M1 start — Feb 16 deadline
04 Feb 2025 | Sprint 1 | Architecture diagram drafted covering all 5 layers | Technology comparison: Twilio vs Azure vs Web Simulator | None | Chose Twilio for native STT
06 Feb 2025 | Sprint 1 | Technology selection complete with justification document | Document all 15 API contracts for /ivr/* endpoints | None
09 Feb 2025 | Sprint 1 | API contracts complete; hospital_db.py with 8 wards created | Build FastAPI skeleton: main.py routers lifespan | None
11 Feb 2025 | Sprint 1 | FastAPI skeleton running; /health and / confirmed HTTP 200 | Implement DTMF routing digits 0-4 | GET /ivr/welcome returned 404 | Fixed: added GET route decorator alongside POST
13 Feb 2025 | Sprint 1 | DTMF routing complete — all 5 options working | Build all 5 IVR flows; test with Twilio | ngrok URL resets on restart | Upgraded to ngrok paid plan
15 Feb 2025 | Sprint 1 | All 5 DTMF flows working; live call verified on Twilio | Final M1 doc review and submission | None | M1 submitted Feb 16
17 Feb 2025 | Sprint 2 | M1 submitted; M3 dev starts | Migrate Gather to speech input; add en-IN hints | None | M3 sprint begins
19 Feb 2025 | Sprint 2 | Speech input working; hints configured; alias map done | Build nlu_service.py with GPT-3.5 | None
21 Feb 2025 | Sprint 2 | GPT NLU working; JSON output confirmed | Implement keyword fallback for GPT failures | OpenAI quota limits during dev | Added fallback proactively
23 Feb 2025 | Sprint 2 | Fallback complete; Polly Aditi voice live | Add SSML: breaks spell-out emphasis prosody | None
25 Feb 2025 | Sprint 2 | SSML complete; all 8 wards tested via live calls | Build session_manager.py with full CRUD | Neurology emphasis threshold bug | Fixed: avail<=2 check corrected
27 Feb 2025 | Sprint 2 | Session manager complete; set/get/retry all working | Implement 4-step admission multi-turn flow | Session key mismatch for name | Fixed: aligned all keys to patient_name
01 Mar 2025 | Sprint 2 | Admission flow complete; all 4 steps tested | Build post-action and call-status handlers | None
02 Mar 2025 | Sprint 2 | M2 and M3 layer complete and confirmed | Begin Sprint 3: security middleware | None | M2 submitted Mar 02
04 Mar 2025 | Sprint 3 | HMAC-SHA1 middleware drafted | Complete middleware: 3-mode config URL reconstruction | Admin endpoints blocked by middleware | Fixed: PROTECTED_PREFIXES changed to /ivr/ only
06 Mar 2025 | Sprint 3 | Security middleware complete; test signatures work | Build retry counter and escalation 3 strikes | None
09 Mar 2025 | Sprint 3 | 3-strike escalation working; DTMF deny confirm fixed | Add confidence gating below 0.65 triggers confirmation | None
11 Mar 2025 | Sprint 3 | Confidence gating done; admin endpoints built | Deploy to Render; configure env vars | Render cold start over 2s | Added lifespan pre-warm
14 Mar 2025 | Sprint 3 | Deployed to Render; health check passes | Configure Twilio webhook to production URL | None
16 Mar 2025 | Sprint 3 | Live calls confirmed on Render; M3 complete | Set up conftest.py and start unit tests | None | M3 submitted Mar 16
18 Mar 2025 | Sprint 4 | conftest.py done; TestRootEndpoints and Welcome tests pass | Write DTMF and Speech intent tests | None
20 Mar 2025 | Sprint 4 | Intent router tests done; 30 TCs passing | Write bed admission status ward admin tests | None
22 Mar 2025 | Sprint 4 | 50 unit tests passing; error and session tests done | Write integration tests: bed 2-turn admission 5-turn | None
24 Mar 2025 | Sprint 4 | Integration tests done; session persistence confirmed | Write E2E tests: happy path DTMF escalation multi-flow | None
26 Mar 2025 | Sprint 4 | All 4 E2E flows passing | Write performance tests: latency load concurrent | None
28 Mar 2025 | Sprint 4 | All tests passing; 67 TCs total | Create Unit Test Plan and Defect Tracker Excel | None
30 Mar 2025 | Sprint 4 | All 3 Excel artifacts complete | Set enforce mode on Render; final M4 submission | None | M4 submitted Mar 30
02 Apr 2025 | Sprint 4 | M4 submitted; production live on Render | Final demo: 4 IVR flows for panel; retrospective | None | Final demo Apr 02

## Retrospection
SPRINT RETROSPECTION ¦ City General Hospital IVR
Sprint | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | Document API contracts before any code is written — prevents mismatches between endpoints and tests. | Using free-tier ngrok for multi-day sessions — URL resets break Twilio webhook silently. | Setting up clean project structure and folder hierarchy on day one — saved time in all later sprints. | Upgraded to ngrok paid plan with fixed domain; planned Render deployment from Sprint 3.
Sprint 2 | Add keyword fallback in every NLU feature before testing on live calls — protects against API quota failures. | Using large OpenAI quota during development without tracking costs — hit quota limit on day 3 of Sprint 2. | Writing GPT system prompts that force strict JSON output — prevented parsing bugs from the very start. | Added keyword fallback proactively; budgeted OpenAI API usage carefully for remaining sprints.
Sprint 3 | Test security middleware against /admin/* routes before deployment — caught the prefix bug before live calls. | Waiting until Sprint 3 to deploy to Render — cold start issues would have been found and fixed earlier. | Building admin monitoring endpoints early — made live call verification and debugging much faster. | Added lifespan pre-warm for Render cold start; set TWILIO_VALIDATION_MODE=enforce from day one in production.
Sprint 4 | Write tests alongside features using TDD — catches session key bugs weeks before the dedicated test sprint. | Writing all tests only in the final sprint — integration bugs found in M4 had been present since M3. | Mocking GPT with unittest.mock.patch from the start — tests run under 50ms and never make real API calls. | Implemented conftest.py session cleanup fixture; noted TDD approach for all future projects.

## Milestone Timeline
MILESTONE TIMELINE ¦ City General Hospital IVR
Milestone | Description | Sprint | Start Date | Due Date | Submitted | Status
Project Start | Team formation subtopic assignment repo setup and initial planning | Pre-Sprint | 02 Feb 2025 | 02 Feb 2025 | 02 Feb 2025 | Completed
Milestone 1 - System Design | Architecture diagrams 5-layer IVR design technology selection justification API contracts for all /ivr/* endpoints hospital data model project plan | Sprint 1 | 02 Feb 2025 | 16 Feb 2025 | 16 Feb 2025 | Completed
Milestone 2 - DTMF Backend | FastAPI app with Twilio TwiML 5 DTMF menu flows hospital mock DB 8 wards 4 patients admin endpoints ngrok and Twilio live deployment | Sprint 1 | 09 Feb 2025 | 02 Mar 2025 | 02 Mar 2025 | Completed
Milestone 3 - Conversational AI | GPT-3.5 NLU keyword fallback Polly Aditi TTS SSML 4-step multi-turn admission session HMAC-SHA1 webhook security 3-strike escalation confidence gating Render deployment | Sprint 2-3 | 16 Feb 2025 | 16 Mar 2025 | 16 Mar 2025 | Completed
Milestone 4 - Testing Deploy | 67-TC unit test plan integration tests E2E tests performance tests defect tracker agile template production deployment with enforce mode | Sprint 4 | 16 Mar 2025 | 30 Mar 2025 | 30 Mar 2025 | Completed
Final Demo - 02 April 2025 | Live demonstration of all 4 IVR flows: full admission DTMF bed check patient status 3-strike escalation. Panel Q&A project retrospective and handover. | Sprint 4 | 30 Mar 2025 | 02 Apr 2025 | 02 Apr 2025 | Completed