## Defect Tracker
DEFECT TRACKER ¦ City General Hospital IVR ¦ All Milestones M1 to M4
Patient Admission and Bed Availability ¦ Infosys BFS Internship ¦ Feb 02 to Apr 02 2025
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Ayush | 02 Feb 2025 | Architecture document missing TTS layer specification — no voice or language details for hospital calls | Sprint 1 | Ayush | Documentation | Added TTS layer section specifying Amazon Polly Aditi en-IN and SSML requirements to architecture doc | 03 Feb 2025 | Closed | Verified in M1 final submission
2 | Ayush | 04 Feb 2025 | API contract for /ivr/admission/* endpoints missing — 4 sub-endpoints not documented before coding | Sprint 1 | Ayush | Documentation | Added all 4 admission sub-endpoint contracts to API contract document before M2 dev started | 05 Feb 2025 | Closed | All 15 endpoints documented
3 | Ayush | 09 Feb 2025 | GET /ivr/welcome returns 404 — Twilio sends GET on first webhook call but only POST was defined | Sprint 1 | Ayush | Routing | Added @router.get decorator alongside POST on /ivr/welcome both route to same welcome_twiml function | 09 Feb 2025 | Closed | TC-006 passes — both GET and POST tested
4 | Ayush | 11 Feb 2025 | Digit 0 transfer to agent silently fails — HOSPITAL_AGENT_NUMBER env var not loaded from .env | Sprint 1 | Ayush | Configuration | Added load_dotenv in main.py lifespan startup verified HOSPITAL_AGENT_NUMBER in Dial tag | 11 Feb 2025 | Closed | TC-013 passes — Dial tag confirmed
5 | Ayush | 13 Feb 2025 | ngrok free tier URL resets on every restart breaking Twilio webhook mid-session | Sprint 1 | Ayush | Infrastructure | Switched to ngrok paid plan with fixed subdomain; later moved to Render for production | 14 Feb 2025 | Closed | Persistent URL used from Sprint 2 onward
6 | Ayush | 14 Feb 2025 | hospital_db.py WARDS dict missing contact_ext key for Emergency ward — KeyError at runtime | Sprint 1 | Ayush | Data | Added contact_ext=911 to Emergency ward entry in WARDS dict | 14 Feb 2025 | Closed | All 8 wards have contact_ext
7 | Ayush | 16 Feb 2025 | GPT system prompt returns unstructured text instead of JSON — nlu_service fails on json.loads | Sprint 2 | Ayush | NLU/AI | Added instruction Return ONLY this JSON no markdown no preamble to system prompt; added regex to strip code fences | 17 Feb 2025 | Closed | TC-021 — GPT returns clean JSON confirmed
8 | Ayush | 18 Feb 2025 | Twilio Gather speechTimeout=2 too short — callers cut off mid-sentence on Indian English names | Sprint 2 | Ayush | Configuration | Changed speechTimeout from 2 to auto on all Gather tags; set timeout=8 on admission/name endpoint | 18 Feb 2025 | Closed | No caller cutoff in test calls after fix
9 | Ayush | 19 Feb 2025 | heart ward and cardiac not recognised as cardiology by keyword fallback — unknown intent returned | Sprint 2 | Ayush | NLU | Added heart cardiac heart ward cardiac ward aliases to WARD_ALIASES dict in nlu_service.py | 19 Feb 2025 | Closed | Alias normalisation confirmed
10 | Ayush | 21 Feb 2025 | Patient not-found endpoint returns HTTP 500 instead of 200 with graceful TwiML message | Sprint 2 | Ayush | Error Handling | Wrapped DB lookup in try/except returns patient_not_found_twiml on any failure — HTTP 200 always | 21 Feb 2025 | Closed | TC-025 — no HTTP 500 on unknown patient
11 | Ayush | 23 Feb 2025 | Admission Step 2 ward handler fails with KeyError if patient name not stored in session | Sprint 2 | Ayush | Logic | Added default=the patient parameter to get_collected call in ward handler; session fails gracefully | 23 Feb 2025 | Closed | TC-050 — empty session ward step reprompts
12 | Ayush | 25 Feb 2025 | SSML say-as spell-out not applied to bed numbers so CAR-04 read as car four instead of C-A-R-zero-four | Sprint 2 | Ayush | SSML/TTS | Wrapped all patient ID and bed number values in spell helper function in twiml_builder.py | 25 Feb 2025 | Closed | TC-030 — spell-out tag confirmed in TwiML
13 | Ayush | 26 Feb 2025 | Neurology ward with 1 available bed not triggering limited-availability SSML emphasis in response | Sprint 2 | Ayush | Logic/SSML | Fixed threshold check: avail less than or equal to 2 now correctly triggers emphasis tag in bed_availability_twiml | 26 Feb 2025 | Closed | TC-046 — emphasis tag confirmed for Neurology
14 | Ayush | 28 Feb 2025 | Confirmation TwiML step 4 does not include patient name from step 2 — session key mismatch | Sprint 2 | Ayush | Session | Fixed typo: set_collected used key patient_name but get_collected used key name — aligned all to patient_name | 28 Feb 2025 | Closed | TC-049 — name appears in confirmation
15 | Ayush | 02 Mar 2025 | TwilioSignatureMiddleware blocks /admin/* endpoints — admin routes are not Twilio webhooks | Sprint 3 | Ayush | Security/Routing | Changed PROTECTED_PREFIXES from / to /ivr/ — admin and health routes now exempt from signature check | 02 Mar 2025 | Closed | TC-037 — admin endpoints accessible without signature
16 | Ayush | 04 Mar 2025 | Retry counter not reset after successful GPT recognition — escalates incorrectly on next speech input | Sprint 3 | Ayush | Logic | Added reset_retry call immediately after successful GPT intent detection in ivr_intent handler | 04 Mar 2025 | Closed | Retry counter resets on success confirmed
17 | Ayush | 07 Mar 2025 | Emergency ward contact extension displayed as 991 in TwiML — typo in hospital_db.py | Sprint 3 | Ayush | Data | Corrected contact_ext from 991 to 911 for Emergency ward in WARDS dict | 07 Mar 2025 | Closed | TC-041 — ext 911 confirmed
18 | Ayush | 09 Mar 2025 | DTMF deny Digits=2 at admission confirm not handled — caller loops back to same confirmation | Sprint 3 | Ayush | Logic | Added elif Digits == 2: return admission_start_twiml branch in /ivr/admission/confirm handler | 09 Mar 2025 | Closed | TC-050 — denial restarts admission confirmed
19 | Ayush | 11 Mar 2025 | conftest.py imports app before setting OPENAI_API_KEY env var — NLU attempts real API call during tests | Sprint 3 | Ayush | Test Infrastructure | Moved os.environ.setdefault calls above the from main import app line in conftest.py | 11 Mar 2025 | Closed | All NLU tests now use mocked GPT — no real API calls
20 | Ayush | 14 Mar 2025 | Render cold start causes first /ivr/welcome to exceed 2000ms latency threshold | Sprint 3 | Ayush | Performance | Added lifespan async context manager in main.py that pre-imports session_manager and hospital_db on startup | 15 Mar 2025 | Closed | TC-057 — subsequent requests under 50ms
21 | Ayush | 16 Mar 2025 | Sample code m4_ivr.py: from fastapi.testclients import TestClient — wrong module name has extra s | Sprint 4 | Ayush | Code Error (Sample) | Corrected import to: from fastapi.testclient import TestClient | 16 Mar 2025 | Closed | Correct import used in all test files
22 | Ayush | 16 Mar 2025 | Sample code m4_ivr.py: import myapp.main import app — invalid Python syntax | Sprint 4 | Ayush | Code Error (Sample) | Corrected to: from main import app | 16 Mar 2025 | Closed | Correct syntax used in all test files
23 | Ayush | 16 Mar 2025 | Sample code m4_ivr.py: paramas= instead of params= in E2E test — test silently sends wrong arguments | Sprint 4 | Ayush | Code Error (Sample) | Corrected typo to params= in all test files | 16 Mar 2025 | Closed | All test files use correct params=
24 | Ayush | 16 Mar 2025 | Sample code m4_ivr.py: TestClient() called without app argument — raises TypeError at runtime | Sprint 4 | Ayush | Code Error (Sample) | Changed to TestClient(app) — app object is required positional argument | 16 Mar 2025 | Closed | All TestClient calls pass app object
25 | Ayush | 16 Mar 2025 | Sample code m4_ivr.py: print with brace placeholders but missing f-string prefix — prints literal braces | Sprint 4 | Ayush | Code Error (Sample) | Added f prefix: f-string used for all print statements in performance tests | 16 Mar 2025 | Closed | f-strings used throughout
26 | Ayush | 18 Mar 2025 | REQ reference number only 4 digits — E2E test regex passes but looks unprofessional for a hospital system | Sprint 4 | Ayush | Logic | Changed random.randint range to 10000-99999 for 5-digit REQ references | 18 Mar 2025 | Closed | TC-048 — REQ with 5 digits generated consistently
27 | Ayush | 21 Mar 2025 | Session state leaks between test cases — retry_count from one test affects next test session | Sprint 4 | Ayush | Test Infrastructure | Added _sessions.clear in conftest.py autouse fixture function-scoped runs before every test | 21 Mar 2025 | Closed | All test classes isolated no session leakage
28 | Ayush | 24 Mar 2025 | Concurrent thread test times out — thread.join timeout=5 too short on slow CI environments | Sprint 4 | Ayush | Testing | Increased join timeout to 10s and reduced concurrent callers from 5 to 3 for reliability | 24 Mar 2025 | Closed | TC-061 — 3 concurrent callers pass consistently
29 | Ayush | 27 Mar 2025 | Production Render deployment TWILIO_VALIDATION_MODE defaults to disabled — insecure for production use | Sprint 4 | Ayush | Security | Set TWILIO_VALIDATION_MODE=enforce in Render environment dashboard verified /security endpoint | 27 Mar 2025 | Closed | TC-066 — production validation_mode=enforce confirmed
30 | Ayush | 29 Mar 2025 | Live Twilio call takes over 3 seconds before welcome message plays — Render free tier cold start | Sprint 4 | Ayush | Performance | Configured Render health check every 5 minutes to keep instance warm; first call now under 2s | 30 Mar 2025 | Closed | TC-067 — live call welcome heard in approx 1.8s

## Summary
DEFECT SUMMARY ¦ All Sprints
Total Defects Logged | 30
Total Closed | 30
Total Open | 0
Sprint 1 — M1 and M2 DTMF | 6
Sprint 2 — M3 AI Layer | 8
Sprint 3 — Security and Deploy | 6
Sprint 4 — M4 Testing | 10
Documentation | 2
Routing | 2
Configuration | 2
NLU/AI | 2
Logic | 4
SSML/TTS | 2
Error Handling | 1
Session | 2
Security | 2
Performance | 2
Test Infrastructure | 2
Code Error (Sample) | 5
Data | 2
Infrastructure | 1